## Gantt Chart Template
Gantt Chart | [27 empty] | https://goo.gl/PXLbMe
| PROJECT TITLE | Quikpik |  |  |  |  | COMPANY NAME | [8 empty] | Quikpik Development Team
| PROJECT MANAGER | Anthony Pham |  |  |  |  | DATE | [8 empty] | 2020-02-19
[7 empty] | SPRINT #0 (2/3 - 2/19) | [14 empty] | SPRINT #1 (2/24 - 3/9) | [14 empty] | SPRINT #2 (3/16 - 4/8) | [14 empty] | SPRINT #3 (4/13 - 4/29)
| TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
PRODUCT BACKLOG
| Set up Environment | Everyone | TBD | TBD | #VALUE! | 0%
| User Login | TBD | TBD | TBD | #VALUE! | 0%
| Main Menu | TBD | TBD | TBD | #VALUE! | 0%
| Log out option | TBD | TBD | TBD | #VALUE! | 0%
| Link Google Map API to App | TBD | TBD | TBD | #VALUE! | 0%
| Link Yelp API to App | TBD | TBD | TBD | #VALUE! | 0%
| User Profile Questionnarire | Everyone | TBD | TBD | #VALUE! | 0%
| Feedback for quikpik (user - > developers) | Everyone | TBD | TBD | #VALUE! | 0%
| User restaurant review (linked to yelp) | TBD | TBD | TBD | #VALUE! | 0%
| Make recommendation AI | TBD | TBD | TBD | #VALUE! | 0%
| Develop AI to be based off of user preferences, habits, location | TBD | TBD | TBD | #VALUE! | 0%
| Develop friend lists, group chats for users | TBD | TBD | TBD | #VALUE! | 0%
SPRINT ZERO
| Learn android studio | Everyone | 2/3/20 | 2/19/20 | 13 | 0%
| Lean how to use APIs from Yelpl Google Maps | Everyone | 2/4/20 | 2/19/20 | 12 | 50% | bar: WEEK 1 W to WEEK 2 W
| Look into building simple prototype to store data in java database | Everyone | 2/5/20 | 2/19/20 | 11 | 100% | bar: WEEK 1 M to WEEK 3 M
| Store user data (database) | Everyone | 2/6/20 | 2/19/20 | 10 | 0%
| Management plan | Everyone | 2/7/20 | 2/17/20 | 7 | 100% | bar: WEEK 2 W to WEEK 3 M
| Learn Firebase | Everyone | 2/8/20 | 2/19/20 | 8 | 0%
| Gantt chart | Everyone | 2/9/20 | 2/17/20 | 6 | 100% | bar: WEEK 3 M
| Feb 5th Presentation slides | Everyone | 2/3/20 | 2/5/20 | 3 | 100% | bar: WEEK 1 M to WEEK 1 W
| Download All Software | Everyone | 2/11/20 | 2/19/20 | 7 | 100% | bar: WEEK 1 M
| Business requirements document | Everyone | 2/12/20 | 2/12/20 | 1 | 100% | bar: WEEK 1 M to WEEK 2 W
| Primary market research | Everyone | 2/3/20 | 2/12/20 | 8 | 100% | bar: WEEK 1 M to WEEK 2 T
SPRINT ONE
Formulas:
DURATION = NETWORKDAYS([START DATE], [DUE DATE])

## Try Smartsheet (hidden)
Try Smartsheet for Free