## Projects
Project Tracking Matrix
|  |  | Service Provider: | Quikpik Development Team
|  |  | Address: | 1250 Bellflower Blvd, Long Beach CA
|  |  | Email: | dev.quikpik@gmail.com
Current Status |  |  | Projects |  | Deliverables |  |  |  | Hours
Status | Date | Priority | Project / Task | Description | Deliverable(s) | Deadline | % Done | Days Left | Est. Hrs | Actual Hrs
- |  | - | Quikpik
Completed | 2020-02-03 | done | Download All Software | Download software to use for project | none | 2020-02-19 | 100% | 0 | 2 | 2
Completed | 2020-02-03 | done | BRD | Business Requirements Document | .pdf file on github | 2020-02-12 | 100% | 0 | 5 | 3
Completed | 2020-02-03 | - | Primary Market Research | Conduct surveys | included in BRD | 2020-02-12 | 100% | 0 | 2 | 1
Completed | 2020-02-03 | done | Learn Android Studio | Get situated with Android Studio basics | none | 2020-02-19 | 100% | 0 | 10 | 7
In Progress | 2020-02-03 | high | Learn APIs | Reasearch how APIs are used and how we can use them | none | 2020-02-19 | 50% | 2 | 10
In Progress | 2020-02-03 | high | Java Server | Create JDBC | files posted to github | 2020-02-19 | 60% | 2 | 5
In Progress | 2020-02-03 | high | Learn Firebase | Google's mobile platform | none | 2020-02-19 | 0% | 2 | 5
In Progress | 2020-02-03 | high | Database | Create a database for user information | sql? files | 2020-02-19 | 55% | 2 | 5
In Progress | 2020-02-03 | high | Connect Firebase server to Android App | Use Firebase | none | 2020-02-19 | 0% | 2 | 6
Planning | 2020-02-03 | high | Set Up Environment | Create a environment where the app can run | none |  |  |  | 7
Planning | 2020-02-03 | high | User Login | username and password | java files on github |  |  |  | 5
Planning | 2020-02-04 | high | Main Menu | select restaurants, user preferences/settings, location settings | java files on github |  |  |  | 2
Planning | 2020-02-05 | high | Log Out option | log out | java files on github |  |  |  | 2
Planning | 2020-02-06 | high | Link APIs | Yelp API & Google Maps? | none |  |  |  | 5
Planning | 2020-02-07 | high | User Profile Questionaire | helps user set food preferences | java files on github |  |  |  | 5
Planning | 2020-02-08 | med | Feedback Hub | to be sent to us so we can improve the application | java files on github |  |  |  | 10
Planning | 2020-02-09 | high | Recommendation AI | chooses locations based on user preferences | java files on github |  |  |  | 50
Planning | 2020-02-10 | low | Add Friends List | basic friends list connectivity | java files on github |  |  |  | 10
- |  | - | Code Design | [5 empty] | x
Planning | 2020-02-11 | med | Create XML for Main Menu | Code the UI main menu in Android Studio |  |  |  |  | 5
Planning | 2020-02-13 | med | Create Java for Main Menu | Code the behavior for the main menu in Android Studio |  |  |  |  | 2
- |  | - | [8 empty] | ◄ Insert new rows above this one
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
- |  | -
Formulas:
Days Left = IF([Deadline]="","",IF([Current Status]="Completed"," - ",[Deadline]-TODAY()))
Days Left = IF([Deadline]="","",IF([Current Status, row above]="Completed"," - ",[Deadline]-TODAY()))

## Settings
Priorities | Status
- | -
high | Planning
med | Pending Approval
low | Approved
done | In Progress
Pending Review
On Hold
Completed

## Help
Help
http://www.vertex42.com/ExcelTemplates/project-tracking-template.html |  | © 2012-2019 Vertex42 LLC
Intro
This template provides a starting point for creating a spreadsheet to help service providers and clients communicate the status of multiple projects and tasks. This project tracking template is meant to be used as a communication tool, not as a substitute for a formal contract.
Using this template
Use Cell Comments
Use cell comments to communicate notes, clarifications, and feedback.
Use Cell Notes
Insert cell notes for long descriptions or explanations.
Conditional Formatting
The spreadsheet uses conditional formatting for the Status, Priority, and Days Left columns, but you can define your own conditional formatting to highlight cells the way you want to.
Additional Help
The link at the top of this worksheet will take you to the web page on vertex42.com that talks about this template.
Related Templates
► Gantt Chart Template
► Project Management Templates
► Business Templates

## ©
Project Tracking Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-tracking-template.html
© 2012-2019 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.